LEAN SIX SIGMA PROCESS MAPPING
AND DATA COLLECTION STRATEGY

Employee Recruitment & Selection Process

DMAIC-Based Define & Measure Foundation

Service / Human Resources Process

Scope: Approved hiring need → candidate acceptance → recruitment-to-onboarding handoff

Submission-ready edited assignment
09 October 2026

Data status: published external benchmarks are identified as external evidence; proposed organizational measures and illustrative VSM values are not presented as an actual company baseline.

# 1. Executive Summary

This assignment develops a Lean Six Sigma process map and data-collection strategy for the employee recruitment and selection process. The process is treated as a service value stream in which information, decisions and candidate records move across hiring managers, recruiters, candidates, HR operations and supporting systems. The improvement objective is not simply to hire faster; it is to reduce avoidable waiting, rework and variation while protecting selection quality, candidate experience, fairness, compliance and stakeholder satisfaction.

The project follows DMAIC. Define establishes the problem, customers, CTQs and boundaries; Measure documents the true current-state process, defines operational measures and validates the measurement system; Analyze will identify statistically supported causes; Improve will pilot future-state changes; and Control will sustain performance through standard work, monitoring and SPC. ASQ identifies process mapping, measurement-system validation, baseline performance and analytical tools as core elements of DMAIC.

The proposed process map contains twelve major stages: need identification, requisition, approval, job design, posting/sourcing, application intake, screening, interview, decision, offer, acceptance and handoff. Waiting and rework are explicitly separated from value-adding work so that the project can determine where total lead time is actually consumed.

External evidence provides context rather than a substitute for an organizational baseline. SHRM's 2026 recruiting benchmark reports a median nonexecutive time-to-fill of 39 calendar days and data from more than 4,600 organizations. The project should compare its verified baseline against such benchmarks only after metric definitions and inclusion rules are aligned.

# 2. Project Charter, Business Case and Scope

| Element | Assignment-specific definition |
| --- | --- |
| Process | Employee recruitment and selection, from approved hiring need/requisition through candidate acceptance and recruitment-to-onboarding handoff. |
| Business problem | Recruitment lead time may contain approval queues, scheduling delays, rework, repeated approvals and inconsistent handoffs. A single time-to-fill value can hide these mechanisms. |
| Problem statement | The process may not consistently move qualified candidates from approved requisition to accepted offer within a predictable lead time, creating avoidable vacancy cost and stakeholder dissatisfaction. |
| Goal statement | Establish a validated current-state map and measurement system that identifies the largest sources of lead-time variation and quality loss. Numeric improvement targets will be set only after the verified baseline is established. |
| Business case | Reducing avoidable waiting and rework can improve staffing responsiveness and process capacity while avoiding the unintended consequence of sacrificing candidate or selection quality. |
| Primary customers | Hiring manager, candidate, HR/recruitment team, business unit and downstream onboarding. |
| Primary CTQs | Predictable speed, candidate responsiveness, selection quality, low rework, process consistency/fairness and complete handoff. |
| Unit of analysis | One eligible requisition/candidate journey with defined process-event timestamps. |
| In scope | Requisition approval through accepted offer and recruitment-to-onboarding handoff. |
| Out of scope | Long-term employee performance management, post-joining compensation administration, workforce planning outside the requisition and external labor-market factors except where they are measurable process inputs. |

## 2.1 DMAIC alignment

| DMAIC phase | How this assignment applies it |
| --- | --- |
| Define | Problem statement, business case, customers, VOC/CTQs, scope, SIPOC and stakeholder roles. |
| Measure | Detailed process map, VSM, operational definitions, data dictionary, sampling plan and measurement-system validation. |
| Analyze | Pareto, stratification, root-cause analysis, FMEA, variation analysis and hypothesis testing/regression where appropriate. |
| Improve | Future-state design, standardization, mistake-proofing, pilot testing and Kaizen-oriented changes. |
| Control | Control plan, SPC/run charts, SOPs, ownership, thresholds and long-term monitoring. |

Methodology basis: ASQ describes DMAIC as a data-driven framework for improving existing processes and connects Measure with documenting the true process, validating measurement systems and establishing a trustworthy baseline.

# 3. External Evidence and Benchmark Context

Published data are used to establish context and demonstrate why the selected CTQs matter. They are not treated as the project's internal baseline. The organization's actual baseline must come from transaction-level recruitment data collected using the definitions in this report.

| Source / evidence | Published finding or methodological contribution | Use in this project |
| --- | --- | --- |
| SHRM 2026 Recruiting Benchmarking | Median nonexecutive time-to-fill = 39 calendar days; report covers >4,600 organizations. Extra-large organizations reported a 67% increase in median requisitions per recruiter; median external filling of nonexecutive positions rose from 93% to 97%. | External benchmark for time-to-fill; workload and sourcing/channel variables become candidate X factors. |
| SHRM 2025 Recruiting Benchmarking | Median recruiting budget was 20% of HR budget; average nonexecutive cost-per-hire $5,475 and executive cost-per-hire $35,879; 20% reported tracking quality of hire. | Supports cost/quality context and the decision to include quality-of-hire as a CTQ. |
| ASQ service case: nursing shift-change | A service process used VSM and DMAIC; reported initial average duration 43 minutes and sigma improvement from 0.7 to 3.3. | Demonstrates that Lean Six Sigma tools can improve service processes, not only manufacturing. |
| ASQ Tata Yazaki AutoComp case | Connects business Y, customer Y, process Y and input/X variables. | Supports the project's X→Y logic: process performance should connect to customer and business outcomes. |
| Lean Enterprise Institute VSM | VSM examines information flow, value-creating/non-value-creating work and current/future states; relevant data include cycle time, lead time, WIP and % complete/accurate. | Basis for separating processing time, waiting time and information handoffs. |
| NIST measurement guidance | Measurement processes should be characterized for repeatability, reproducibility, stability and uncertainty; process monitoring uses statistical control methods. | Basis for timestamp audits, attribute-agreement checks and later control charts. |

Benchmark caution: SHRM statistics come from external survey/benchmark populations and should not be presented as the organization's performance. Published figures are contextual evidence only.

# 4. SIPOC + Constraints + Measures

SIPOC is used before the detailed process map to establish process boundaries and identify upstream inputs and downstream customers.

| Suppliers | Inputs | High-level process | Outputs | Customers |
| --- | --- | --- | --- | --- |
| Business unit / hiring manager | Approved headcount; role requirement | 1. Identify need | Approved requisition | Hiring manager |
| Finance | Budget / cost authorization | 2. Approve requisition | Validated job description | Finance / leadership |
| HR policy owners | Recruitment policy; compliance rules | 3. Design role | Candidate pipeline | HR/recruitment |
| Candidates | Applications; availability; information | 4. Post/source | Shortlist | Candidate |
| Job platforms / sourcing channels | Candidate traffic | 5. Receive applications | Interview decisions | Business unit |
| Recruiter / HR | Screening and interview criteria | 6. Screen | Offer | Onboarding |
| Interview panel | Assessment evidence | 7. Interview → 8. Select | Accepted candidate | Organization |

| +C: Constraints | +M: Measures |
| --- | --- |
| Budget and approval limits | Time-to-fill / lead time |
| Recruiter workload and WIP | Stage cycle time |
| Interview-panel availability | Waiting/queue time |
| Candidate availability | First-pass yield / rework rate |
| Policy, legal and privacy requirements | Offer acceptance |
| ATS/system availability | Candidate experience |
| Data quality and handoff requirements | Quality-of-hire proxy; data completeness |

# 5. Detailed Current-State Process Map

The detailed map decomposes the recruitment journey into measurable activities and decision points. It is a proposed current-state structure and must be validated through a process walk with recruiters, hiring managers and HR operations before being treated as the definitive work-as-done map.

| Step | Process activity | Primary output | Lean/Six Sigma annotation | Key measure |
| --- | --- | --- | --- | --- |
| 1 | Need identified | Hiring need | Customer demand / input | Demand date; request completeness |
| 2 | Requisition created | Requisition | Defect risk if incomplete | Requisition revision count |
| 3 | Approval | Authorized requisition | WAITING / queue | Approval lead time; 90th percentile |
| 4 | Job design | Validated JD + criteria | Defect prevention / CTQ definition | JD revisions; approval-to-post |
| 5 | Posting & sourcing | Candidate pipeline | Channel variation / overproduction risk | Applicants by source; qualified yield |
| 6 | Application intake | Candidate records | INVENTORY / WIP | Queue size; completeness |
| 7 | Screening | Shortlist | Variation / rework risk | Screen cycle; first-pass yield |
| 8 | Interview | Assessment evidence | WAITING / scheduling | Scheduling lead time; interview cycle |
| 9 | Decision | Selected candidate | Decision delay / variation | Decision turnaround; reschedule rate |
| 10 | Offer | Offer issued | Rework if approval/details incomplete | Offer processing; revisions |
| 11 | Acceptance | Accepted/declined | Failure demand / drop-off | Acceptance rate; offer-to-accept |
| 12 | Handoff | Onboarding-ready record | Defect if fields are incomplete | Handoff completeness; correction rate |

# 6. Value-Stream Mapping and Lean Waste Analysis

Value-stream mapping provides the end-to-end view needed to distinguish active processing from waiting. For recruitment, the flow is primarily information and decision flow: ATS → recruiter → hiring manager/interview panel → candidate → HR/onboarding.

Important: any processing/waiting values shown in the VSM graphic are illustrative placeholders. They must be replaced with timestamp-derived organizational values during Measure.

| VSM concept | Recruitment equivalent | Data to collect |
| --- | --- | --- |
| Cycle time | Actual active work time | Observed/reliably logged processing minutes |
| Lead time | Requisition opening → accepted offer | Start/end timestamps |
| Waiting time | Approval, scheduling, decision and queue delays | Queue entry/exit timestamps |
| % Complete & Accurate | Correct requisition/application/handoff at first submission | First-pass / completeness check |
| WIP | Candidates or requisitions waiting at a stage | Queue count and queue age |
| Information flow | ATS, recruiter, hiring manager, panel, candidate, onboarding | Handoffs and system events |

## 6.1 Lean waste hypotheses

| Waste | Recruitment example | Test metric |
| --- | --- | --- |
| Waiting | Approval, interview scheduling, offer approval | Median and 90th-percentile queue time |
| Defects | Incomplete requisitions, missing data, incorrect screening | Rework rate; first-pass yield |
| Overprocessing | Duplicate entry / repeated approvals | Handoffs, system entries and approvals per case |
| Motion | Searching across multiple systems | Observed minutes and system switches |
| Inventory | Candidate/requisition queues | WIP count and queue age |
| Underutilized talent | Professional time spent on avoidable administration | Administrative minutes / total process time |
| Overproduction | Large volumes of unqualified applicants | Qualified applicant yield by channel |

# 7. CTQ Tree and X → Y Measurement Architecture

| Customer need | CTQ | Y metric | Desired direction |
| --- | --- | --- | --- |
| Timely staffing | Predictable speed | Time-to-fill; stage lead time; 90th percentile | Lower / more predictable |
| Responsive candidate journey | Responsiveness | Median candidate response interval | Lower |
| Accurate selection | Selection quality | Qualified-to-interview yield; offer acceptance; quality-of-hire proxy | Higher |
| Efficient HR execution | Low rework | First-pass yield; rework rate; missing-field rate | Higher FPY / lower rework |
| Fair/consistent process | Consistency and transparency | Documentation completeness; lawful/job-related subgroup comparisons where appropriate | Consistent / transparent |

Six Sigma framing: the project asks which process inputs (Xs) explain variation in the output measures (Ys), rather than assuming that the process is slow for one generic reason.

| Potential X (input/cause) | Expected Y affected | How measured |
| --- | --- | --- |
| Approval delay | Time-to-fill / approval-stage lead time | Approval requested/completed timestamps |
| Recruiter workload / WIP | Stage lead time | Open requisitions per recruiter; queue age |
| Interview-panel availability | Interview scheduling lead time | Request-to-confirm timestamps; panel size |
| Job family / role complexity | Time-to-fill / screening yield | Controlled categorical variable |
| Sourcing channel | Qualified yield / offer acceptance | Source + downstream disposition |
| Number of interview rounds | Time-to-fill / candidate experience | Count of required rounds |
| Requisition revisions | Rework / time-to-fill | Revision count and reason |
| Candidate response time | Offer-to-accept / overall lead time | Candidate-facing event timestamps |
| Offer approval time | Offer processing / time-to-fill | Offer approval and issue timestamps |

# 8. Detailed Data Collection Strategy

Data collection must create a trustworthy baseline before root-cause analysis. The preferred source is transaction-level ATS/HRIS data supplemented by structured observation and standardized feedback. Each variable must have one operational definition, one source of truth and a documented validation rule.

| Metric / variable | Type | Operational definition | Source | Method | Sampling |
| --- | --- | --- | --- | --- | --- |
| Time-to-fill | Continuous | Offer acceptance timestamp − requisition opening timestamp | ATS/HRIS | Automated timestamp calculation | Census of eligible cases |
| Approval lead time | Continuous | Final approval − approval request | ATS/workflow | Timestamp difference | Census |
| Posting lead time | Continuous | Posting live − final approval | ATS/career site | Timestamp difference | Census |
| Screening cycle | Continuous | Screen completion − application receipt | ATS | Timestamp difference | Census or systematic sample if extreme volume |
| Interview scheduling lead time | Continuous | Confirmed interview − interview request | ATS/calendar + observation | Timestamp + validation sample | Stratified by role family/panel format |
| Rework count | Discrete | Returns/revisions before step acceptance | Workflow history | Check sheet + system history | Census |
| First-pass yield | Proportion | Eligible transactions accepted without correction/rework | Workflow history | Binary coding | Census |
| Offer acceptance | Proportion | Accepted offers ÷ formally issued offers | ATS | Automated status | Census |
| Candidate experience | Ordinal | Standardized post-process rating | Survey | 5-point Likert + comment | Systematic sample of closed candidates |
| Handoff completeness | Proportion | Required fields complete and valid at handoff | ATS/HRIS | Validation rule | Census |
| Quality-of-hire proxy | Ordinal/continuous | Predefined 90-day outcome measure where available | HRIS/manager survey | Standardized score | Cohort sample |
| Data completeness | Proportion | Valid required fields ÷ required fields expected | ATS/HRIS | Automated quality report | Census |

## 8.1 Required master dataset

| Field group | Required fields |
| --- | --- |
| Identifiers | Requisition ID; candidate-process ID where permitted; no unnecessary PII |
| Organization | Job family; department; position level; hiring type; recruiter/process owner |
| Process timestamps | Requisition opened; approval requested/completed; posting live; application received; screening started/completed; interview requested/scheduled/completed; decision; offer approval/issue; acceptance/decline; handoff |
| Funnel counts | Applicants; screened; interviewed; offered; accepted |
| Cause / attribute fields | Source/channel; requisition revision count; rework flag/reason; delay reason; interview rounds/panel format |
| Quality fields | Candidate experience score; handoff completeness; quality-of-hire measure; data completeness |

## 8.2 Sampling design

| Data stream | Recommended design | Reason |
| --- | --- | --- |
| ATS/HRIS | 12-month historical census if available; otherwise 3–6 months plus prospective capture | Captures seasonality, role mix and normal process variation |
| Manual time study | Stratify by recruiter and job family; observe different days/times | Prevents one person/time period from representing the process |
| Candidate survey | Systematic sample of closed candidates; monitor nonresponse bias | Captures VOC without requiring a census |
| Interview scheduling | Stratify by panel size, role family and interview format | Scheduling complexity may create major waiting time |
| Quality-of-hire follow-up | Cohort sample with predefined follow-up point | Links process inputs to downstream outcomes without changing definitions |

# 9. Measurement-System Validation / MSA

NIST's measurement-process framework emphasizes repeatability, reproducibility and stability. In this service process, the 'measurement system' consists of ATS/HRIS timestamps, workflow definitions, data extraction logic and human classification. The goal is to ensure that observed variation reflects the recruitment process rather than inconsistent measurement.

| Measurement risk | Validation activity | Acceptance / decision logic |
| --- | --- | --- |
| Timestamp reliability | Audit sample against source-system history; distinguish system-generated from manually entered fields | No unexplained timestamp shifts; documented exceptions |
| Rework classification | Two independent reviewers classify the same cases using the written definition | Agreement calculated; systematic disagreement triggers definition revision |
| Survey consistency | Pilot survey; test wording and response-scale interpretation | Remove ambiguous items; standardize administration |
| Extraction stability | Repeat extraction and reconcile record counts/key fields | Counts and key values reconcile within documented tolerance |
| Process definition stability | Walk-through with process owners | All owners agree on start/stop events and exception rules |
| Missing data | Report missingness by field, recruiter, role family and period | Characterize missingness before exclusion or imputation |

For attribute measures such as rework yes/no, an attribute-agreement study is an appropriate service-process analogue to a Gage R&R study. For automated timestamps, the emphasis is on data lineage, field reliability and stability rather than physical-gauge repeatability.

# 10. Statistical and Lean Analysis Plan

| Tool | Use in this project | Decision supported |
| --- | --- | --- |
| SIPOC | Define boundaries, suppliers, inputs, outputs and customers | What belongs in scope? |
| Detailed process map | Expose tasks, decisions, handoffs and failure points | Where can delay/rework enter? |
| VSM | Separate processing from waiting across the end-to-end flow | Where is lead time consumed? |
| Check sheet / data dictionary | Standardize event capture and classifications | Can the same event be measured consistently? |
| Descriptive statistics | Mean, median, SD, IQR, min/max, 90th percentile | What does the distribution look like? |
| Histogram / box plot | Examine skew and variation | Are some roles/stages highly variable? |
| Pareto | Rank delay, rework and drop-off categories | Which few causes dominate? |
| Run / control chart | Monitor performance over time | Is the process stable or changing? |
| Stratification | Compare job family, recruiter, source, interview structure | Where is variation concentrated? |
| Cause-and-effect / 5 Whys | Structure possible root causes | Which causes should be tested? |
| FMEA | Rate failure modes by severity, occurrence and detectability | Which risks deserve prevention first? |
| Hypothesis tests / regression | Test associations after data/assumption checks | Which X variables are statistically associated with Y? |

## 10.1 Analysis sequence

Verify process boundaries, operational definitions and inclusion/exclusion rules.

Extract the agreed dataset and perform record-count, duplicate, missingness and timestamp-validity checks.

Calculate stage-level descriptive statistics and distinguish active processing from waiting.

Build Pareto charts for delay, rework and candidate drop-off reasons.

Stratify by legitimate process variables such as job family, recruiter/process owner and sourcing channel.

Use run/control charts where data volume and measurement structure support them.

Use hypothesis tests or regression only after checking data type, independence, confounding and sample adequacy.

Use validated findings to construct the future-state map and prioritize improvements.

Pilot changes on a defined subset and compare pre/post performance while monitoring quality and candidate experience.

Transfer successful changes into the Control plan.

# 11. Future-State Improvement Design

The following are improvement hypotheses, not claims that the current organization already has these problems. They should be prioritized only after Measure/Analyze confirms the relevant failure modes.

| Improvement | Lean/Six Sigma rationale | Measure after pilot |
| --- | --- | --- |
| Single owner for each handoff + queue expectation | Reduce waiting and unclear ownership | Queue time; 90th percentile |
| Standardized requisition and interview criteria | Prevent defects and downstream rework | Revision rate; first-pass yield |
| Automated event timestamps | Reduce measurement ambiguity and manual entry | Timestamp completeness |
| Structured interview scorecards | Reduce avoidable decision variation | Scorecard completeness; panel agreement |
| Exception codes | Separate true special causes from normal flow | Exception frequency and resolution time |
| Dashboard separating processing vs waiting | Target the actual mechanism of delay | Active vs waiting time |
| Required fields / validation rules | Mistake-proof common data defects | Missing-field rate; rework rate |
| Speed + quality paired metrics | Prevent a faster but lower-quality process | Time-to-fill + quality-of-hire + candidate experience |

# 12. Control Plan

| Metric | Owner | Frequency | Control signal | Response |
| --- | --- | --- | --- | --- |
| Time-to-fill / stage lead time | Recruitment operations | Weekly/monthly | Sustained shift or validated threshold breach | Review bottleneck stage and top delay reasons |
| First-pass yield | Process owner | Weekly | Decline below agreed baseline/target | Audit recent rework cases; identify failure mode |
| Offer acceptance | Recruitment lead | Monthly | Unexpected decline / channel shift | Review offer process, candidate feedback and role/source mix |
| Handoff completeness | HR operations | Weekly | Critical missing-field rate above threshold | Correct record and investigate upstream defect |
| Candidate experience | Recruitment lead | Monthly | Sustained decline / complaint cluster | VOC review and targeted process investigation |
| Data completeness | Data/system owner | Weekly | Missingness or extraction reconciliation failure | Stop automated reporting if data integrity is compromised |

Control limits and alert thresholds must be calculated from the verified baseline and selected using an appropriate statistical method; they should not be invented merely to make the dashboard appear precise.

# 13. Process-Map and Data-Quality Review Plan

| Checkpoint | Reviewers | What is checked | Evidence/output |
| --- | --- | --- | --- |
| Map walk-through | Recruiter + hiring manager + HR operations | Actual sequence, exceptions, handoffs and decision rules | Approved current-state map |
| Data-definition review | Process owner + analyst | Start/stop events, units, inclusion/exclusion rules | Approved data dictionary |
| Pilot extraction | Data analyst + system owner | Counts, duplicates, missing fields, timestamp logic | Data-quality log |
| Measurement agreement study | Two or more reviewers | Consistency of manual classifications | Agreement results + revised definitions if needed |
| Baseline review | Project lead + sponsor | Denominators, verified data and interpretation | Baseline dashboard |
| Stakeholder validation | HR + business + candidate-experience representative where appropriate | Business meaning and unintended consequences | Validated problem statement and CTQs |

Do not delete unusual records simply because they are inconvenient; determine whether they are data errors, legitimate special causes or valid exceptions.

Maintain an audit trail from source field → transformation rule → derived metric.

Freeze metric definitions before comparing groups or pre/post periods.

Use only legitimate process/business variables for subgroup analysis and protect sensitive information.

Validate the map against observed work, not only written SOPs.

# 14. Assignment Requirement Traceability

| Assignment requirement | How this edited report satisfies it |
| --- | --- |
| Deconstruct a chosen service/manufacturing process | Recruitment is decomposed into 12 measurable stages with outputs, decisions, waste and measurement points. |
| Clear process map using flowcharts/SIPOC/VSM | SIPOC+CM, detailed process map and value-stream view are included. |
| Robust measurement/data collection | Operational definitions, master dataset, sources, methods, sampling and validation are specified. |
| Types/sources/measurement techniques/sampling | ATS/HRIS timestamps, workflow logs, observation, survey and HRIS quality data are defined with sampling designs. |
| Lean Six Sigma concepts | Waiting, WIP/inventory, defects, overprocessing, motion, first-pass yield, CTQ, X→Y, FMEA, DMAIC, mistake-proofing and SPC are explicitly applied. |
| Public sources/frameworks | ASQ, SHRM, Lean Enterprise Institute and NIST are used as methodology/benchmark evidence. |
| Statistical integration | Descriptive statistics, Pareto, stratification, control/run charts and conditional hypothesis/regression analysis are planned. |
| Validation/review | Measurement-system validation, attribute agreement, extraction reconciliation, map walk-through and stakeholder review are included. |
| Analytical thinking | The report distinguishes published benchmarks, proposed measurement design, illustrative values and the future organizational baseline. |
| Practicality | The plan prioritizes existing ATS/HRIS timestamps and a census where feasible, reducing unnecessary manual collection. |

# 15. References and Public Frameworks

American Society for Quality (ASQ). DMAIC Process: Define, Measure, Analyze, Improve, Control. https://asq.org/quality-resources/dmaic

American Society for Quality (ASQ). SIPOC+CM Diagram. https://asq.org/quality-resources/sipoc

American Society for Quality (ASQ). Six Sigma Tools & Techniques. https://asq.org/quality-resources/sixsigma/tools

American Society for Quality (ASQ). Using DMAIC to Improve Nursing Shift-Change Assignments. https://asq.org/quality-resources/articles/case-studies/using-dmaic-to-improve-nursing-shift-change-assignments

American Society for Quality (ASQ). Six Sigma: The Critical Link between Process Improvements and Business Results (Tata Yazaki AutoComp). https://asq.org/quality-resources/articles/case-studies/six-sigma-the-critical-link-between-process-improvements-and-business-results

Lean Enterprise Institute. Value-Stream Mapping Overview. https://www.lean.org/lexicon-terms/value-stream-mapping/

Lean Enterprise Institute. Keep It Simple: Value-Stream Mapping at the Gemba. https://www.lean.org/the-lean-post/articles/keep-it-simple-value-stream-map-at-the-gemba/

NIST/SEMATECH. Engineering Statistics Handbook, Chapter 2: Measurement Process Characterization. https://www.nist.gov/publications/nistsematech-engineering-statistics-handbook-chapter-2-measurement-process

NIST/SEMATECH. Engineering Statistics Handbook, Chapter 6: Process or Product Monitoring and Control. https://www.nist.gov/publications/nistsematech-engineering-statistics-handbook-chapter-6-process-or-product-monitoring

Society for Human Resource Management (SHRM). 2026 Recruiting Benchmarking: Attracting Critical Talent. https://www.shrm.org/topics-tools/research/recruiting-benchmarking

Society for Human Resource Management (SHRM). 2025 Recruiting Benchmarking Report. https://www.shrm.org/content/dam/en/shrm/research/2025-recruiting-benchmarking-report.pdf

# Appendix A. Example Data-Collection Form

| Field | Example / allowed value | Validation |
| --- | --- | --- |
| Requisition ID | REQ-000123 | Unique; nonblank |
| Job family | Finance / HR / Operations / IT / Other | Controlled list |
| Requisition opened | YYYY-MM-DD HH:MM | Must precede approval |
| Approval completed | YYYY-MM-DD HH:MM | Cannot precede opening |
| Posting live | YYYY-MM-DD HH:MM | Cannot precede final approval |
| Application received | YYYY-MM-DD HH:MM | Valid within process window or exception coded |
| Screen completed | YYYY-MM-DD HH:MM | Cannot precede application |
| Interview completed | YYYY-MM-DD HH:MM | Must follow screening where required |
| Decision recorded | YYYY-MM-DD HH:MM | Must follow interview where required |
| Offer issued | YYYY-MM-DD HH:MM | Must follow decision |
| Offer outcome | Accepted / Declined / Withdrawn / Expired | Controlled list |
| Handoff complete | YYYY-MM-DD HH:MM | Required fields complete |
| Rework flag | 0 / 1 | Definition documented |
| Delay reason | Approval / Scheduling / Candidate / System / Other | Primary code + optional secondary |

# Appendix B. Key Formulas

Time-to-fill = Offer acceptance timestamp − requisition opening timestamp.

Stage cycle time = Stage completion timestamp − stage start timestamp.

Waiting time = Lead time − active processing time, where active processing time is measured consistently.

First-pass yield = Transactions completed without rework ÷ total eligible transactions × 100.

Rework rate = Transactions requiring correction/revision ÷ total eligible transactions × 100.

Offer acceptance rate = Accepted offers ÷ offers issued × 100.

Handoff completeness = Complete handoffs ÷ total handoffs × 100.

Data completeness = Populated valid required fields ÷ total required fields expected × 100.

# Appendix C. Data Status and Interpretation Rules

| Data category | Status in this assignment | How it must be used |
| --- | --- | --- |
| SHRM benchmarks | Published external data | Context/benchmark only; not the organization's baseline |
| ASQ/LEI/NIST evidence | Published methodology/case evidence | Justifies methods and Lean Six Sigma design |
| Process map / SIPOC | Project-designed representation | Must be validated against work-as-done |
| Illustrative VSM values | Illustrative only | Demonstrate measurement structure; never report as actual results |
| Proposed dataset and KPIs | Measurement design | Used to collect the actual organizational baseline |
| Actual organizational baseline | Not available in the supplied material | Must be calculated from verified ATS/HRIS/observation data |